## Sheet1
ID | Risk Description | Category | Likelihood (L) | Impact (L) | Risk Rating | Owner | Mitigation Strategy | Status | Comment
R1 | Unclear requirements may cause rework | Process | Medium | High | 12 | Product Owner | Conduct backlog refinement workshops; clarify acceptance criteria | Open | Needs continuous backlog refinement to reduce ambiguity.
R2 | Key developer unavailable due to illness | Operational | High | Medium | 15 | Scrum Master | Cross-train team members; maintain knowledge sharing | Open | Ensure backup resource plan is in place.
R3 | Integration with external API may fail | Technical | Medium | High | 12 | Dev Team Lead | Create mock API; plan early integration testing | Mitigated | Early API testing reduced the impact significantly.
R4 | Vendor delay in delivering components | External | Low | High | 8 | Product Owner | Maintain alternative suppliers; adjust Sprint scope | Open | Monitor vendor closely; risk remains open.
R5 | Performance issues in production | Technical | Medium | Medium | 9 | QA Lead | Conduct load testing; optimise code before release | Open | Performance testing scheduled; risk under observation.